## Project Planner
Binan Information Kiosk Development
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | OCTOBER
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Research and Planning
Research | 2 | 5 | 2 | 5 | 100%
Project Planning | 2 | 5 | 2 | 6 | 90%
Proposal Presentation | 2 | 1 | 2 | 1 | 100%
Gather Materials | 2 | 4 | 3 | 3 | 55%
Solution Designing
Site Mapping | 3 | 2 | 2 | 1 | 90%
Module Designing | 3 | 3 | 4 | 9 | 70%
Module Development
Home Module | 3 | 7 | 3 | 4 | 80%
Search Module | 3 | 10 | 9 | 30 | 45%
Map Module | 5 | 30 | 6 | 30 | 30%